## Answer Report 1
Microsoft Excel 12.0 Answer Report
Worksheet: [PERT-CPM - Ex. 1 - Alternativa.xls]Sheet1
Report Created: 20-02-2011 23:13:25
Target Cell (Min)
| Cell | Name | Original Value | Final Value
| $J$23 | Custo Total= Duração | 0 | 140
Adjustable Cells
| Cell | Name | Original Value | Final Value
| $I$5 | A(1,2) Inicio | 0 | 0
| $I$6 | B(2,3) Inicio | 0 | 2
| $I$7 | C(3,4) Inicio | 0 | 6
| $I$8 | D(4,5) Inicio | 0 | 16
| $I$9 | E(4,6) Inicio | 0 | 16
| $I$10 | Fic1(6,7) Inicio | 0 | 20
| $I$11 | F(6,9) Inicio | 0 | 20
| $I$12 | G(5,7) Inicio | 0 | 22
| $I$13 | H(7,8) Inicio | 0 | 29
| $I$14 | I(4,9) Inicio | 0 | 16
| $I$15 | J(9,10) Inicio | 0 | 23
| $I$16 | K(10,11) Inicio | 0 | 30
| $I$17 | Fic2(11,12) Inicio | 0 | 34
| $I$18 | L(10,12) Inicio | 0 | 29
| $I$19 | M(8,13) Inicio | 0 | 38
| $I$20 | N(12,13) Inicio | 0 | 34
| $J$5 | A(1,2) Duração | 0 | 0
| $J$6 | B(2,3) Duração | 0 | 0
| $J$7 | C(3,4) Duração | 0 | 0
| $J$8 | D(4,5) Duração | 0 | 0
| $J$9 | E(4,6) Duração | 0 | 0
| $J$10 | Fic1(6,7) Duração | 0 | 0
| $J$11 | F(6,9) Duração | 0 | 2
| $J$12 | G(5,7) Duração | 0 | 0
| $J$13 | H(7,8) Duração | 0 | 0
| $J$14 | I(4,9) Duração | 0 | 0
| $J$15 | J(9,10) Duração | 0 | 2
| $J$16 | K(10,11) Duração | 0 | 0
| $J$17 | Fic2(11,12) Duração | 0 | 0
| $J$18 | L(10,12) Duração | 0 | 0
| $J$19 | M(8,13) Duração | 0 | 0
| $J$20 | N(12,13) Duração | 0 | 0
| $J$22 | Data Fim= Duração | 0 | 40
Constraints
| Cell | Name | Cell Value | Formula | Status | Slack
| $M$5 | A(1,2) | 2 | $M$5>=$C$5 | Binding | 0
| $M$6 | B(2,3) | 4 | $M$6>=$C$6 | Binding | 0
| $M$7 | C(3,4) | 10 | $M$7>=$C$7 | Binding | 0
| $M$8 | D(4,5) | 6 | $M$8>=$C$8 | Binding | 0
| $M$9 | E(4,6) | 4 | $M$9>=$C$9 | Binding | 0
| $M$10 | Fic1(6,7) | 9 | $M$10>=$C$10 | Not Binding | 9
| $M$11 | F(6,9) | 5 | $M$11>=$C$11 | Binding | 0
| $M$12 | G(5,7) | 7 | $M$12>=$C$12 | Binding | 0
| $M$13 | H(7,8) | 9 | $M$13>=$C$13 | Binding | 0
| $M$14 | I(4,9) | 7 | $M$14>=$C$14 | Binding | 0
| $M$15 | J(9,10) | 9 | $M$15>=$C$15 | Not Binding | 1
| $M$16 | K(10,11) | 4 | $M$16>=$C$16 | Binding | 0
| $M$17 | Fic2(11,12) | 0 | $M$17>=$C$17 | Binding | 0
| $M$18 | L(10,12) | 5 | $M$18>=$C$18 | Binding | 0
| $M$19 | M(8,13) | 2 | $M$19>=$C$19 | Binding | 0
| $M$20 | N(12,13) | 6 | $M$20>=$C$20 | Binding | 0
| $N$7 | C(3,4) Restrições | 10 | $N$7>=$C$7 | Binding | 0
| $O$7 | C(3,4) | 10 | $O$7>=$C$7 | Binding | 0
| $N$9 | E(4,6) Restrições | 4 | $N$9>=$C$9 | Binding | 0
| $N$15 | J(9,10) Restrições | 8 | $N$15>=$C$15 | Binding | 0
| $J$5 | A(1,2) Duração | 0 | $J$5<=$G$5 | Not Binding | 1
| $J$6 | B(2,3) Duração | 0 | $J$6<=$G$6 | Not Binding | 2
| $J$7 | C(3,4) Duração | 0 | $J$7<=$G$7 | Not Binding | 3
| $J$8 | D(4,5) Duração | 0 | $J$8<=$G$8 | Not Binding | 2
| $J$9 | E(4,6) Duração | 0 | $J$9<=$G$9 | Not Binding | 1
| $J$10 | Fic1(6,7) Duração | 0 | $J$10<=$G$10 | Binding | 0
| $J$11 | F(6,9) Duração | 2 | $J$11<=$G$11 | Binding | 0
| $J$12 | G(5,7) Duração | 0 | $J$12<=$G$12 | Not Binding | 3
| $J$13 | H(7,8) Duração | 0 | $J$13<=$G$13 | Not Binding | 3
| $J$14 | I(4,9) Duração | 0 | $J$14<=$G$14 | Not Binding | 2
| $J$15 | J(9,10) Duração | 2 | $J$15<=$G$15 | Binding | 0
| $J$16 | K(10,11) Duração | 0 | $J$16<=$G$16 | Not Binding | 1
| $J$17 | Fic2(11,12) Duração | 0 | $J$17<=$G$17 | Binding | 0
| $J$18 | L(10,12) Duração | 0 | $J$18<=$G$18 | Not Binding | 2
| $J$19 | M(8,13) Duração | 0 | $J$19<=$G$19 | Not Binding | 1
| $J$20 | N(12,13) Duração | 0 | $J$20<=$G$20 | Not Binding | 3
| $J$22 | Data Fim= Duração | 40 | $J$22<=40 | Binding | 0

## Sensitivity Report 1
Microsoft Excel 12.0 Sensitivity Report
Worksheet: [PERT-CPM - Ex. 1 - Alternativa.xls]Sheet1
Report Created: 20-02-2011 23:13:26
Adjustable Cells
|  |  | Final | Reduced | Objective | Allowable | Allowable
| Cell | Name | Value | Cost | Coefficient | Increase | Decrease
| $I$5 | A(1,2) Inicio | 0 | 50 | 0 | 1e+30 | 50
| $I$6 | B(2,3) Inicio | 2 | 0 | 0 | 50 | 50
| $I$7 | C(3,4) Inicio | 6 | 0 | 0 | 10 | 0
| $I$8 | D(4,5) Inicio | 16 | 0 | 0 | 0 | 40
| $I$9 | E(4,6) Inicio | 16 | 0 | 0 | 10 | 0
| $I$10 | Fic1(6,7) Inicio | 20 | 0 | 0 | 10 | 0
| $I$11 | F(6,9) Inicio | 20 | 0 | 0 | 10 | 0
| $I$12 | G(5,7) Inicio | 22 | 0 | 0 | 0 | 40
| $I$13 | H(7,8) Inicio | 29 | 0 | 0 | 0 | 60
| $I$14 | I(4,9) Inicio | 16 | 0 | 0 | 0 | 0
| $I$15 | J(9,10) Inicio | 23 | 0 | 0 | 20 | 0
| $I$16 | K(10,11) Inicio | 30 | 0 | 0 | 0 | 0
| $I$17 | Fic2(11,12) Inicio | 34 | 0 | 0 | 0 | 0
| $I$18 | L(10,12) Inicio | 29 | 0 | 0 | 50 | 0
| $I$19 | M(8,13) Inicio | 38 | 0 | 0 | 0 | 100
| $I$20 | N(12,13) Inicio | 34 | 0 | 0 | 50 | 10
| $J$5 | A(1,2) Duração | 0 | 50 | 100 | 1e+30 | 50
| $J$6 | B(2,3) Duração | 0 | 0 | 50 | 0 | 10
| $J$7 | C(3,4) Duração | 0 | 30 | 80 | 1e+30 | 30
| $J$8 | D(4,5) Duração | 0 | 40 | 40 | 1e+30 | 40
| $J$9 | E(4,6) Duração | 0 | 110 | 160 | 1e+30 | 110
| $J$10 | Fic1(6,7) Duração | 0 | 0 | 0 | 1e+30 | 0
| $J$11 | F(6,9) Duração | 2 | -10 | 40 | 10 | 1e+30
| $J$12 | G(5,7) Duração | 0 | 40 | 40 | 1e+30 | 40
| $J$13 | H(7,8) Duração | 0 | 60 | 60 | 1e+30 | 60
| $J$14 | I(4,9) Duração | 0 | 30 | 30 | 1e+30 | 30
| $J$15 | J(9,10) Duração | 2 | -20 | 30 | 20 | 1e+30
| $J$16 | K(10,11) Duração | 0 | 40 | 40 | 1e+30 | 40
| $J$17 | Fic2(11,12) Duração | 0 | 0 | 0 | 1e+30 | 0
| $J$18 | L(10,12) Duração | 0 | 0 | 50 | 1e+30 | 0
| $J$19 | M(8,13) Duração | 0 | 100 | 100 | 1e+30 | 100
| $J$20 | N(12,13) Duração | 0 | 10 | 60 | 1e+30 | 10
| $J$22 | Data Fim= Duração | 40 | -50 | 0 | 50 | 1e+30
Constraints
|  |  | Final | Shadow | Constraint | Allowable | Allowable
| Cell | Name | Value | Price | R.H. Side | Increase | Decrease
| $M$5 | A(1,2) | 2 | 50 | 2 | 2 | 0
| $M$6 | B(2,3) | 4 | 50 | 4 | 2 | 0
| $M$7 | C(3,4) | 10 | 0 | 10 | 0 | 1e+30
| $M$8 | D(4,5) | 6 | 0 | 6 | 0 | 1e+30
| $M$9 | E(4,6) | 4 | 50 | 4 | 2 | 0
| $M$10 | Fic1(6,7) | 9 | 0 | 0 | 9 | 1e+30
| $M$11 | F(6,9) | 5 | 50 | 5 | 2 | 0
| $M$12 | G(5,7) | 7 | 0 | 7 | 0 | 1e+30
| $M$13 | H(7,8) | 9 | 0 | 9 | 0 | 1e+30
| $M$14 | I(4,9) | 7 | 0 | 7 | 0 | 1e+30
| $M$15 | J(9,10) | 9 | 0 | 8 | 1 | 1e+30
| $M$16 | K(10,11) | 4 | 0 | 4 | 1 | 1e+30
| $M$17 | Fic2(11,12) | 0 | 0 | 0 | 1 | 1e+30
| $M$18 | L(10,12) | 5 | 50 | 5 | 2 | 0
| $M$19 | M(8,13) | 2 | 0 | 2 | 0 | 1e+30
| $M$20 | N(12,13) | 6 | 50 | 6 | 2 | 0
| $N$7 | C(3,4) Restrições | 10 | 50 | 10 | 2 | 0
| $O$7 | C(3,4) | 10 | 0 | 10 | 0 | 1e+30
| $N$9 | E(4,6) Restrições | 4 | 0 | 4 | 9 | 20
| $N$15 | J(9,10) Restrições | 8 | 50 | 8 | 2 | 0

## Sheet1
Cap. 1 - Exercício 1. Projecto da RELIABLE CONSTRUCTION. i)
|  | Duração | (semanas) | Custo (1000$) |  | Redução | Custo Aceler. | Data | Redução | Data
| Activid. | Normal | Acelerada | Normal | Acelerado | Máxima | Unit. ($) | Inicio | Duração | Fim |  | Restrições
| A(1,2) | 2 | 1 | 180 | 280 | 1 | 100 | 0 | 0 | 2 | 2
| B(2,3) | 4 | 2 | 320 | 420 | 2 | 50 | 2 | 0 | 6 | 4
| C(3,4) | 10 | 7 | 620 | 860 | 3 | 80 | 6 | 0 | 16 | 10 | 10 | 10
| D(4,5) | 6 | 4 | 260 | 340 | 2 | 40 | 16 | 0 | 22 | 6
| E(4,6) | 4 | 3 | 410 | 570 | 1 | 160 | 16 | 0 | 20 | 4 | 4
| Fic1(6,7) | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 9
| F(6,9) | 5 | 3 | 180 | 260 | 2 | 40 | 20 | 2 | 23 | 5
| G(5,7) | 7 | 4 | 900 | 1020 | 3 | 40 | 22 | 0 | 29 | 7
| H(7,8) | 9 | 6 | 200 | 380 | 3 | 60 | 29 | 0 | 38 | 9
| I(4,9) | 7 | 5 | 210 | 270 | 2 | 30 | 16 | 0 | 23 | 7
| J(9,10) | 8 | 6 | 430 | 490 | 2 | 30 | 23 | 2 | 29 | 9 | 8
| K(10,11) | 4 | 3 | 160 | 200 | 1 | 40 | 30 | 0 | 34 | 4
| Fic2(11,12) | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 34 | 0
| L(10,12) | 5 | 3 | 250 | 350 | 2 | 50 | 29 | 0 | 34 | 5
| M(8,13) | 2 | 1 | 100 | 200 | 1 | 100 | 38 | 0 | 40 | 2
| N(12,13) | 6 | 3 | 330 | 510 | 3 | 60 | 34 | 0 | 40 | 6
[8 empty] | Data Fim= | 40
[8 empty] | Custo Total= | 140

## Answer Report 2
Microsoft Excel 12.0 Answer Report
Worksheet: [PERT-CPM - Ex. 1 - Alternativa.xls]Sheet2
Report Created: 20-02-2011 23:14:53
Target Cell (Max)
| Cell | Name | Original Value | Final Value
| $J$23 | Lucro Adicional= Duração | 1175 | 75
Adjustable Cells
| Cell | Name | Original Value | Final Value
| $I$5 | A(1,2) Inicio | 0 | 0
| $I$6 | B(2,3) Inicio | 0 | 2
| $I$7 | C(3,4) Inicio | 0 | 6
| $I$8 | D(4,5) Inicio | 0 | 20
| $I$9 | E(4,6) Inicio | 0 | 16
| $I$10 | Fic1(6,7) Inicio | 0 | 33
| $I$11 | F(6,9) Inicio | 0 | 20
| $I$12 | G(5,7) Inicio | 0 | 26
| $I$13 | H(7,8) Inicio | 0 | 33
| $I$14 | I(4,9) Inicio | 0 | 16
| $I$15 | J(9,10) Inicio | 0 | 25
| $I$16 | K(10,11) Inicio | 0 | 34
| $I$17 | Fic2(11,12) Inicio | 0 | 38
| $I$18 | L(10,12) Inicio | 0 | 33
| $I$19 | M(8,13) Inicio | 0 | 42
| $I$20 | N(12,13) Inicio | 0 | 38
| $J$5 | A(1,2) Duração | 0 | 0
| $J$6 | B(2,3) Duração | 0 | 0
| $J$7 | C(3,4) Duração | 0 | 0
| $J$8 | D(4,5) Duração | 0 | 0
| $J$9 | E(4,6) Duração | 0 | 0
| $J$10 | Fic1(6,7) Duração | 0 | 0
| $J$11 | F(6,9) Duração | 0 | 0
| $J$12 | G(5,7) Duração | 0 | 0
| $J$13 | H(7,8) Duração | 0 | 0
| $J$14 | I(4,9) Duração | 0 | 0
| $J$15 | J(9,10) Duração | 0 | 0
| $J$16 | K(10,11) Duração | 0 | 0
| $J$17 | Fic2(11,12) Duração | 0 | 0
| $J$18 | L(10,12) Duração | 0 | 0
| $J$19 | M(8,13) Duração | 0 | 0
| $J$20 | N(12,13) Duração | 0 | 0
| $J$22 | Data Fim= Duração | 0 | 44
Constraints
| Cell | Name | Cell Value | Formula | Status | Slack
| $M$5 | A(1,2) | 2 | $M$5>=$C$5 | Binding | 0
| $M$6 | B(2,3) | 4 | $M$6>=$C$6 | Binding | 0
| $M$7 | C(3,4) | 14 | $M$7>=$C$7 | Not Binding | 4
| $M$8 | D(4,5) | 6 | $M$8>=$C$8 | Binding | 0
| $M$9 | E(4,6) | 4 | $M$9>=$C$9 | Binding | 0
| $M$10 | Fic1(6,7) | 0 | $M$10>=$C$10 | Binding | 0
| $M$11 | F(6,9) | 5 | $M$11>=$C$11 | Binding | 0
| $M$12 | G(5,7) | 7 | $M$12>=$C$12 | Binding | 0
| $M$13 | H(7,8) | 9 | $M$13>=$C$13 | Binding | 0
| $M$14 | I(4,9) | 9 | $M$14>=$C$14 | Not Binding | 2
| $M$15 | J(9,10) | 9 | $M$15>=$C$15 | Not Binding | 1
| $M$16 | K(10,11) | 4 | $M$16>=$C$16 | Binding | 0
| $M$17 | Fic2(11,12) | 0 | $M$17>=$C$17 | Binding | 0
| $M$18 | L(10,12) | 5 | $M$18>=$C$18 | Binding | 0
| $M$19 | M(8,13) | 2 | $M$19>=$C$19 | Binding | 0
| $M$20 | N(12,13) | 6 | $M$20>=$C$20 | Binding | 0
| $N$7 | C(3,4) Restrições | 10 | $N$7>=$C$7 | Binding | 0
| $C$7 | C(3,4) Normal | 10 | $C$7>=$C$7 | Binding | 0
| $O$7 | C(3,4) | 10 | $O$7>=$C$7 | Binding | 0
| $N$9 | E(4,6) Restrições | 17 | $N$9>=$C$9 | Not Binding | 13
| $N$15 | J(9,10) Restrições | 8 | $N$15>=$C$15 | Binding | 0
| $G$5 | A(1,2) Máxima | 1 | $G$5<=$G$5 | Binding | 0
| $G$6 | B(2,3) Máxima | 2 | $G$6<=$G$6 | Binding | 0
| $G$7 | C(3,4) Máxima | 3 | $G$7<=$G$7 | Binding | 0
| $G$8 | D(4,5) Máxima | 2 | $G$8<=$G$8 | Binding | 0
| $G$9 | E(4,6) Máxima | 1 | $G$9<=$G$9 | Binding | 0
| $G$10 | Fic1(6,7) Máxima | 0 | $G$10<=$G$10 | Binding | 0
| $G$11 | F(6,9) Máxima | 2 | $G$11<=$G$11 | Binding | 0
| $G$12 | G(5,7) Máxima | 3 | $G$12<=$G$12 | Binding | 0
| $G$13 | H(7,8) Máxima | 3 | $G$13<=$G$13 | Binding | 0
| $G$14 | I(4,9) Máxima | 2 | $G$14<=$G$14 | Binding | 0
| $G$15 | J(9,10) Máxima | 2 | $G$15<=$G$15 | Binding | 0
| $G$16 | K(10,11) Máxima | 1 | $G$16<=$G$16 | Binding | 0
| $G$17 | Fic2(11,12) Máxima | 0 | $G$17<=$G$17 | Binding | 0
| $G$18 | L(10,12) Máxima | 2 | $G$18<=$G$18 | Binding | 0
| $G$19 | M(8,13) Máxima | 1 | $G$19<=$G$19 | Binding | 0
| $G$20 | N(12,13) Máxima | 3 | $G$20<=$G$20 | Binding | 0
| $J$22 | Data Fim= Duração | 44 | $J$22<=47 | Not Binding | 3

## Sensitivity Report 2
Microsoft Excel 12.0 Sensitivity Report
Worksheet: [PERT-CPM - Ex. 1 - Alternativa.xls]Sheet2
Report Created: 20-02-2011 23:14:55
Adjustable Cells
|  |  | Final | Reduced | Objective | Allowable | Allowable
| Cell | Name | Value | Cost | Coefficient | Increase | Decrease
| $I$5 | A(1,2) Inicio | 0 | -25 | 0 | 25 | 1e+30
| $I$6 | B(2,3) Inicio | 2 | 0 | 0 | 25 | 75
| $I$7 | C(3,4) Inicio | 6 | 0 | 0 | 25 | 25
| $I$8 | D(4,5) Inicio | 20 | 0 | 0 | 25 | 0
| $I$9 | E(4,6) Inicio | 16 | 0 | 0 | 25 | 25
| $I$10 | Fic1(6,7) Inicio | 33 | 0 | 0 | 0 | 0
| $I$11 | F(6,9) Inicio | 20 | 0 | 0 | 25 | 25
| $I$12 | G(5,7) Inicio | 26 | 0 | 0 | 25 | 0
| $I$13 | H(7,8) Inicio | 33 | 0 | 0 | 25 | 0
| $I$14 | I(4,9) Inicio | 16 | 0 | 0 | 0 | 25
| $I$15 | J(9,10) Inicio | 25 | 0 | 0 | 25 | 15
| $I$16 | K(10,11) Inicio | 34 | 0 | 0 | 0 | 0
| $I$17 | Fic2(11,12) Inicio | 38 | 0 | 0 | 0 | 0
| $I$18 | L(10,12) Inicio | 33 | 0 | 0 | 25 | 5
| $I$19 | M(8,13) Inicio | 42 | 0 | 0 | 25 | 0
| $I$20 | N(12,13) Inicio | 38 | 0 | 0 | 25 | 5
| $J$5 | A(1,2) Duração | 0 | -75 | -100 | 75 | 1e+30
| $J$6 | B(2,3) Duração | 0 | -25 | -50 | 25 | 1e+30
| $J$7 | C(3,4) Duração | 0 | -55 | -80 | 55 | 1e+30
| $J$8 | D(4,5) Duração | 0 | -40 | -40 | 40 | 1e+30
| $J$9 | E(4,6) Duração | 0 | -135 | -160 | 135 | 1e+30
| $J$10 | Fic1(6,7) Duração | 0 | 0 | 0 | 0 | 1e+30
| $J$11 | F(6,9) Duração | 0 | -15 | -40 | 15 | 1e+30
| $J$12 | G(5,7) Duração | 0 | -40 | -40 | 40 | 1e+30
| $J$13 | H(7,8) Duração | 0 | -60 | -60 | 60 | 1e+30
| $J$14 | I(4,9) Duração | 0 | -30 | -30 | 30 | 1e+30
| $J$15 | J(9,10) Duração | 0 | -5 | -30 | 5 | 1e+30
| $J$16 | K(10,11) Duração | 0 | -40 | -40 | 40 | 1e+30
| $J$17 | Fic2(11,12) Duração | 0 | 0 | 0 | 0 | 1e+30
| $J$18 | L(10,12) Duração | 0 | -25 | -50 | 25 | 1e+30
| $J$19 | M(8,13) Duração | 0 | -100 | -100 | 100 | 1e+30
| $J$20 | N(12,13) Duração | 0 | -35 | -60 | 35 | 1e+30
| $J$22 | Data Fim= Duração | 44 | 0 | -25 | 25 | 5
Constraints
|  |  | Final | Shadow | Constraint | Allowable | Allowable
| Cell | Name | Value | Price | R.H. Side | Increase | Decrease
| $M$5 | A(1,2) | 2 | -25 | 2 | 3 | 2
| $M$6 | B(2,3) | 4 | -25 | 4 | 3 | 6
| $M$7 | C(3,4) | 14 | 0 | 10 | 4 | 1e+30
| $M$8 | D(4,5) | 6 | 0 | 6 | 4 | 1e+30
| $M$9 | E(4,6) | 4 | -25 | 4 | 3 | 2
| $M$10 | Fic1(6,7) | 0 | 0 | 0 | 13 | 1e+30
| $M$11 | F(6,9) | 5 | -25 | 5 | 3 | 2
| $M$12 | G(5,7) | 7 | 0 | 7 | 4 | 1e+30
| $M$13 | H(7,8) | 9 | 0 | 9 | 4 | 1e+30
| $M$14 | I(4,9) | 9 | 0 | 7 | 2 | 1e+30
| $M$15 | J(9,10) | 9 | 0 | 8 | 1 | 1e+30
| $M$16 | K(10,11) | 4 | 0 | 4 | 1 | 1e+30
| $M$17 | Fic2(11,12) | 0 | 0 | 0 | 1 | 1e+30
| $M$18 | L(10,12) | 5 | -25 | 5 | 3 | 1
| $M$19 | M(8,13) | 2 | 0 | 2 | 4 | 1e+30
| $M$20 | N(12,13) | 6 | -25 | 6 | 3 | 4
| $N$7 | C(3,4) Restrições | 10 | -25 | 10 | 3 | 2
| $C$7 | C(3,4) Normal | 10 | 0 | 10 | 0 | 1e+30
| $O$7 | C(3,4) | 10 | 0 | 10 | 2 | 16
| $N$9 | E(4,6) Restrições | 17 | 0 | 4 | 13 | 1e+30
| $N$15 | J(9,10) Restrições | 8 | -25 | 8 | 3 | 1
| $G$5 | A(1,2) Máxima | 1 | 0 | 1 | 1e+30 | 0
| $G$6 | B(2,3) Máxima | 2 | 0 | 2 | 1e+30 | 0
| $G$7 | C(3,4) Máxima | 3 | 0 | 3 | 1e+30 | 0
| $G$8 | D(4,5) Máxima | 2 | 0 | 2 | 1e+30 | 0
| $G$9 | E(4,6) Máxima | 1 | 0 | 1 | 1e+30 | 0
| $G$10 | Fic1(6,7) Máxima | 0 | 0 | 0 | 1e+30 | 0
| $G$11 | F(6,9) Máxima | 2 | 0 | 2 | 1e+30 | 0
| $G$12 | G(5,7) Máxima | 3 | 0 | 3 | 1e+30 | 0
| $G$13 | H(7,8) Máxima | 3 | 0 | 3 | 1e+30 | 0
| $G$14 | I(4,9) Máxima | 2 | 0 | 2 | 1e+30 | 0
| $G$15 | J(9,10) Máxima | 2 | 0 | 2 | 1e+30 | 0
| $G$16 | K(10,11) Máxima | 1 | 0 | 1 | 1e+30 | 0
| $G$17 | Fic2(11,12) Máxima | 0 | 0 | 0 | 1e+30 | 0
| $G$18 | L(10,12) Máxima | 2 | 0 | 2 | 1e+30 | 0
| $G$19 | M(8,13) Máxima | 1 | 0 | 1 | 1e+30 | 0
| $G$20 | N(12,13) Máxima | 3 | 0 | 3 | 1e+30 | 0

## Sheet2
Cap. 1 - Exercício 1. Projecto da RELIABLE CONSTRUCTION. j)
|  | Duração | (semanas) | Custo (1000$) |  | Redução | Custo Aceler. | Data | Redução | Data
| Activid. | Normal | Acelerada | Normal | Acelerado | Máxima | Unit. ($) | Inicio | Duração | Fim |  | Restrições
| A(1,2) | 2 | 1 | 180 | 280 | 1 | 100 | 0 | 0 | 2 | 2
| B(2,3) | 4 | 2 | 320 | 420 | 2 | 50 | 2 | 0 | 6 | 4
| C(3,4) | 10 | 7 | 620 | 860 | 3 | 80 | 6 | 0 | 16 | 14 | 10 | 10
| D(4,5) | 6 | 4 | 260 | 340 | 2 | 40 | 20 | 0 | 26 | 6
| E(4,6) | 4 | 3 | 410 | 570 | 1 | 160 | 16 | 0 | 20 | 4 | 17
| Fic1(6,7) | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 33 | 0
| F(6,9) | 5 | 3 | 180 | 260 | 2 | 40 | 20 | 0 | 25 | 5
| G(5,7) | 7 | 4 | 900 | 1020 | 3 | 40 | 26 | 0 | 33 | 7
| H(7,8) | 9 | 6 | 200 | 380 | 3 | 60 | 33 | 0 | 42 | 9
| I(4,9) | 7 | 5 | 210 | 270 | 2 | 30 | 16 | 0 | 23 | 9
| J(9,10) | 8 | 6 | 430 | 490 | 2 | 30 | 25 | 0 | 33 | 9 | 8
| K(10,11) | 4 | 3 | 160 | 200 | 1 | 40 | 34 | 0 | 38 | 4
| Fic2(11,12) | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 0 | 38 | 0
| L(10,12) | 5 | 3 | 250 | 350 | 2 | 50 | 33 | 0 | 38 | 5
| M(8,13) | 2 | 1 | 100 | 200 | 1 | 100 | 42 | 0 | 44 | 2
| N(12,13) | 6 | 3 | 330 | 510 | 3 | 60 | 38 | 0 | 44 | 6
[8 empty] | Data Fim= | 44
[8 empty] | Lucro Adicional= | 75