## Sheet2
|  | BA | DE | DS | WD | Risk | w1 | w2 | w3 | w4 | w5 | w6 | w7 | w8 | w9 | w10 | w11 | w12 | w13 | w14 | Tools and Resource
1 | Business Understanding
1.1. | Define Business Objectives
1.2. | Identify ethical values and privacy | A/R |  |  |  | L | [14 empty] | meeting Tool
1.3. | Assess Situation | A/R |  |  |  | L | [14 empty] | meeting Tool
1.4. | Define Data Science Goals | A/R |  |  |  | L | [14 empty] | meeting Tool
1.5. | Produce Project Plan | A/R | R | R |  | L | [14 empty] | WBS, GANTT
2 | Data Understanding
2.1. | Collect Initial Data |  | A/R |  |  | H | [14 empty] | open data, scraping,
2.2. | Describe Data |  | A/R |  |  | L | [14 empty] | use Jupyter/python/Pandas
2.3. | Explore Data |  | A/R |  |  | M | [14 empty] | use Jupyter/python/Pandas
2.4. | Verify Data Quality |  |  | A/R |  | H | [14 empty] | use Jupyter/python/Pandas
3 | Data Preparation |  |  | A/R
3.1. | Select Data |  |  | A/R |  | M | [14 empty] | Meeting
3.2. | Clean Data |  |  | A/R |  | M | [14 empty] | use Jupyter/python/Pandas
3.3. | Construct Data |  |  | A/R |  | M | [14 empty] | use Jupyter/python/Pandas
3.4. | Integrate Data |  |  | A/R |  | H | [14 empty] | use Jupyter/python/Pandas
3.4. | Format Data |  |  | A/R |  | H | [14 empty] | use Jupyter/python/Pandas
4 | Modeling
4.1. | Select Modeling Techniques | I |  | A/R |  | H | [14 empty] | MIT flowchart
4.2. | Generate Test Design | I |  | A/R |  | H | [14 empty] | use Jupyter/python/Pandas
4.3. | Build Model | I |  | A/R |  | M | [14 empty] | use Jupyter/python/Pandas
4.4. | Assess Model | I |  | A/R |  | H | [14 empty] | use Jupyter/python/Pandas
5 | Evaluation
5.1. | Evaluate Results, icnluding ethical | A/R |  | R |  | H | [14 empty] | use Jupyter/python/Pandas
5.2. | Review Process | A/R |  |  |  | L | [14 empty] | meeting Tool
5.3. | Determine Next Steps | A/R |  |  |  | L | [14 empty] | meeting Tool
6 | Deployment
6.1. | Plan Deployment | A |  | R | R | H | [14 empty] | PowerBI or Flash
6.2. | Plan Monitoring and Maintenance | A |  |  |  | M | [14 empty] | meeting Tool
6.3. | Produce Final Report | A/R | R | R | R | M | [14 empty] | PowerBI or Flash
6.4. | Review Project | A/R |  | R |  | M | [14 empty] | meeting Tool